## Summary
Question | Answer
Is the original ADR document still relevant? | Yes. It is the live decision record, not a historical artefact. 63 of 77 ADRs are in force or extended by a later one. It is append-only by design: later ADRs refine, extend or supersede earlier ones, and the file was kept up to date through ADR-077 (this sprint).
Is it fully current? | No. 7 ADRs are formally superseded (whole or in part), 3 are only partly built, 2 are not built, 2 are deferred by the owner. Four headers (ADR-019, 032, 033, 037) still read plain 'Accepted' although a later ADR or event changed their meaning (see 'Stale headers').
Does it need replacing? | No. A rewrite would lose the reasoning and the trade-offs, which are the point of an ADR. Recommended: a one-line status edit on four headers, and keep this register as the shareable index.
What is this workbook? | A register of all 77 ADRs with each one's standing today, relevance, whether it is built, and what supersedes or extends it. It is an index and an assessment, not a new decision. The decisions themselves stay in docs/adr/architecture-decisions.md.
How the 'standing' was decided | ADR headers and the 'Supersedes / Extends' lines were read mechanically. ADRs 001-037 that carry no override are marked Active on the strength of the ADR header and the absence of a contradicting later ADR; that is NOT a re-check against the code. The overrides (for example 'not built' or 'deferred') come from CLAUDE.md and projectContextForMe.md.
Not covered | Sprints that made no architectural decision have no ADR by design. Work not yet run: nothing in the mobile programme (ADR-072 to 077) has run on a device, an EAS build or a store console; nothing is deployed.
Generated | From docs/adr/architecture-decisions.md at the Sprint 66 commit (c7c7d7c).
Standing today | ADRs
Active | 63
Superseded in part | 6
Partly built | 3
Planned – not built | 2
Deferred by owner | 2
Superseded | 1

## ADR Register
ADR | Title | Date | Sprint | Migration | Standing today | Relevance | Built? | Decision (from the ADR) | Status line as written | Related ADRs | Superseded / carried on by | Assessment note | Basis for the assessment
ADR-001 | Overall Product Architecture |  |  |  | Active | High | Built | Adopt layered architecture: 1. Marketplace Layer (CRUD, transactions) 2. Intelligence Layer (AI + graph + scoring) | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-002 | Backend Technology Stack |  |  |  | Active | High | Built | Use Python + FastAPI | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-003 | Database Choice |  |  |  | Active | High | Built | Use PostgreSQL + pgvector | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-004 | Skill Taxonomy |  |  |  | Active | High | Built | Adopt NSQF-aligned skill taxonomy with multi-framework support | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-005 | AI Strategy |  |  |  | Planned – not built | Medium | Not built | Use hybrid AI: 1. LLM for extraction & explanation 2. Deterministic logic for decision-making | Accepted |  |  | No LLM call exists anywhere; the intelligence/ module has an ADR and no code. The direction stands: ADR-036 keeps every decision deterministic and lets a model only explain. | CLAUDE.md ('Not built')
ADR-006 | Event-Driven Architecture |  |  |  | Active | High | Built | Adopt event-driven architecture with async workers | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-007 | Matching Engine Design |  |  |  | Active | High | Built | Hybrid scoring: 1. Skill overlap (primary) 2. Semantic similarity 3. Experience | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-008 | Career Path Engine |  | 42 |  | Superseded in part | Medium | Partly built | Graph-based role transition engine | Accepted. First slice built in Sprint 42 as ADR-049, derived from qualification data rather than the graph below. | ADR-049 | ADR-049 | First slice delivered by ADR-049: ladders are derived at read time from qualification data and nothing is stored. The inference graph this ADR describes is unbuilt (SkillRelation has no edges). | ADR-008 header; CLAUDE.md careers/
ADR-009 | Authentication Architecture |  |  |  | Active | High | Built | Centralized identity service with JWT | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-010 | Multi-Tenant Design |  |  |  | Active | High | Built | Global users + tenant + membership model | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-011 | Identity Model |  |  |  | Partly built | Medium | Partly built | Use UUID as primary identity; Aadhaar as optional verification | Accepted |  |  | UUID primary key built. Optional Aadhaar verification is not built and nothing collects Aadhaar data. | CLAUDE.md; ADR-023
ADR-012 | RBAC vs ABAC |  |  |  | Active | High | Built | Start with RBAC, design for ABAC | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-013 | Embedding Strategy |  |  |  | Partly built | Medium | Partly built | Use sentence-transformers + pgvector | Accepted |  |  | pgvector storage and a 384-dimension port are built (ADR-031). The mandated sentence-transformers model is not switched on: HashingEmbeddingProvider is an honest placeholder and BL-5.3 is not started. | CLAUDE.md adapters/embeddings
ADR-014 | Deployment Strategy |  |  |  | Active | High | Built | Start with modular monolith → evolve to microservices | Accepted |  |  | Modular monolith in place; a later split into services has not been needed or done. | CLAUDE.md
ADR-015 | Target Market Strategy | September 2026 |  |  | Superseded | Low | n/a | India-first, single-sector rollout | Superseded by ADR-024 (September 2026) | ADR-024 | ADR-024 | Replaced by ADR-024 (taxonomy-first, multi-sector, India-first). | ADR-015 header
ADR-016 | API Architecture |  |  |  | Active | High | Built | API-first architecture using REST initially. | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-017 | Integration Architecture |  |  |  | Active | High | Built | All external systems accessed through provider adapters. | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-018 | AI Model Strategy |  |  |  | Planned – not built | Medium | Not built | Use external LLMs. | Accepted |  |  | No external LLM is integrated. The adapter pattern it depends on exists (ADR-017, ADR-031). | CLAUDE.md ('Not built')
ADR-019 | Observability Strategy |  |  |  | Superseded in part | Medium | Partly built | Adopt: Structured logging Metrics Distributed tracing | Accepted |  | ADR-040 | Tooling half replaced by ADR-040 (structured JSON logs to stdout). The destination (OpenTelemetry, Prometheus, Grafana) remains deferred and unbuilt. | ADR-040 header
ADR-020 | Caching Strategy |  |  |  | Active | High | Built | Redis-based caching | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-021 | Search Architecture |  |  |  | Active | High | Built | PostgreSQL search | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-022 | Authorization Scope |  |  |  | Active | High | Built | Permission-based authorization | Accepted |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-023 | Data Privacy & Compliance |  |  |  | Partly built | High | Partly built | Encrypted data | Accepted |  |  | Consent record, DPDP export, erasure, the redaction filter and retention are built. The encryption path for Aadhaar, resumes and assessment results is not, so that data is deliberately not collected. | CLAUDE.md; ADR-055, ADR-067
ADR-024 | Sector Rollout Scope | September 2026 |  |  | Active – supersedes ADR-015 | High | Built | Multi-sector from the outset, taxonomy-first. Supersedes ADR-015. | Accepted (September 2026) |  |  | Supersedes ADR-015. | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-025 | Monetization Model | September 2026 |  |  | Deferred by owner | Medium | Not built | v1 is free to all actors. The revenue model is deferred pending traction data. | Accepted (September 2026) |  |  | Monetisation (BL-1.3) is a standing not-started: the owner chose to wait for real traffic. ADR-043 and ADR-047 carry the deferral. | ADR-043, ADR-047; projectContextForMe.md
ADR-026 | Supply Acquisition Strategy | September 2026 |  |  | Active | High | Built | Hybrid — operations-curated seeding alongside provider self-serve publishing. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-027 | Async Task Runner | September 2026 |  |  | Active | High | Built | Use ARQ as the task runner. Amends ADR-006. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-028 | Cloud Platform and Deployment Topology | September 2026 |  |  | Deferred by owner | Medium | Not built | AWS ap-south-1 (Mumbai), ECS Fargate, infrastructure defined in Terraform. | Accepted (September 2026) |  |  | Nothing is deployed anywhere; deployment is deferred by the owner and is now on the mobile launch's critical path. Still the intended topology. | projectContextForMe.md section 0
ADR-029 | Client Architecture | September 2026 |  |  | Active | High | Built | A single Next.js progressive web application, mobile-first. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-030 | Identity Implementation — Build versus Buy | September 2026 |  |  | Active | High | Built | Build the identity service in-house. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-031 | AI Provider Abstraction and Embedding Dimensionality | September 2026 |  |  | Active | High | Built | LLMProvider and EmbeddingProvider adapter protocols with multiple implementations, and a platform embedding dimension pinned at 384. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-032 | Primary Credential by Actor Type | September 2026 |  |  | Superseded in part | Medium | Built | Phone with one-time passcode for candidates; email and password for organizational actors. Both linkable on a single account. | Accepted (September 2026) |  | ADR-038 | The organisation half (email OTP, password-free) is replaced by ADR-038; the credential-follows-actor rule still governs sign-up. | ADR-038 header
ADR-033 | Language Scope at Launch | September 2026 |  |  | Superseded in part | Medium | Built | Hindi and English both live at launch. | Accepted (September 2026) |  | ADR-041 | The two-language assumption is replaced by ADR-041 (a language is a messages file and rows). Hindi and English remain the launch pair; Malay is hidden from the switcher, not removed. | ADR-041 header
ADR-034 | NSQF Source of Record | September 2026 |  |  | Active | High | Built | MongoDB is the source of record for the raw NSQF feed. PostgreSQL remains the operational store, into which the feed is projected by an importer. The relationship is one-directional and the projection is re-runnable. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-035 | Selective Ingestion of the NSQF Master Data | September 2026 |  |  | Active | High | Built | Ingestion is selective and justified per collection, not wholesale. The ssc collection is not imported at all, and no module under api/ may read it. More generally: a field is imported because something needs it, not because it is present. Audit, workflow and shadow fields (createdBy, updatedReason, Reviews, dockets, deactivation, every _bk / _Old variant) are dropped by the document parsers rather than carried… | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-036 | Recommendation Approach and Where the LLM Sits | September 2026 |  |  | Active | High | Built | 1. Recommendations are skill-based. Behaviour is a re-ranker, never a source of matches. 2. LLM calls happen at write time, never in the request path. | Accepted (September 2026) |  |  |  | ADR header; no later ADR contradicts it (not re-checked against code)
ADR-037 | The Employer Console as a Labelled Demonstration | September 2026 |  |  | Superseded in part | Medium | Built | ship the employer console as an unauthenticated demonstration, bounded by three constraints that are enforced in code rather than promised in a document. 1. It is the same scorer, run the other way round. score_match takes what a job requires and what a person holds; it does not care which side the query started from. Ranking candidates is that function with its arguments swapped. No second scoring implementation… | Accepted (September 2026) |  | ADR-038 | The rule that no employer-facing payload identifies a candidate stands and is tested. The 'unauthenticated demonstration' framing no longer describes the product: the authenticated employer console shipped to production in Sprint 12 (ADR-038); only the unauthenticated demo console is local-only. | CLAUDE.md Sprint 11/12 entries
ADR-038 | One Identity, Many Roles | September 2026 |  |  | Active – supersedes part of ADR-032 | High | Built | 1. Organisations sign in with email and a one-time passcode. No passwords anywhere in the product. ADR-032's principle is kept intact and is what the code implements: which credential a flow requires is decided by actor type in the service layer, not scattered across handlers. 2. One User, many Membership rows. A signed-in person can create an organisation from their existing identity (POST /me/organisations) and… | Accepted (September 2026). Supersedes the organisational half of ADR-032. | ADR-032 |  | Supersedes the organisation half of ADR-032. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-039 | Authorization — Permissions Resolved From Membership Role | September 2026 |  |  | Active – extends earlier ADR | High | Built | a permission layer whose permissions are resolved from the membership role. - Callers ask for a permission, never for a role — ADR-022 — so ADR-012's eventual move to ABAC changes how the set is computed without touching a single route. - The set is a closed StrEnum, for the same reason EVENT_NAMES is closed: an open string becomes forty spellings of the same idea within a month, and no audit survives that. -… | Accepted (September 2026). Implements ADR-012 and ADR-022. | ADR-012, ADR-022 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-040 | Structured JSON logging, superseding ADR-019's tooling |  |  |  | Active – supersedes part of ADR-019 | High | Built | structured JSON to stdout, one object per line, no vendor SDK. - One structlog.stdlib.ProcessorFormatter on one root handler, so structlog-native records and stdlib records — uvicorn, ARQ, SQLAlchemy, the notification adapters — render through one shared tail and land in one stream. - The redaction filter ADR-023 has always specified lives in that shared tail, which is what makes it unbypassable: reaching for… | Accepted. Supersedes the tooling half of ADR-019, which remains the destination. | ADR-019 |  | Supersedes the tooling half of ADR-019. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-041 | Localisation — source text in the row, translations in one table | September 2026 |  |  | Active – supersedes part of ADR-033 | High | Built | 1. The base column holds the text in the row's own language. title_en becomes title; name_en becomes name. A source_locale column (default en) says which language that is, because a job posted by a Hindi-speaking employer is source-Hindi and the corpus is source-English. 2. Every other language lives in content_translations — (entity_type, entity_id, field, locale, text, source), unique on the first four. Adding… | Accepted (September 2026). Supersedes the two-language assumption in ADR-033, whose India-first, Hindi-and-English-at-launch decision stands; what is withdrawn is the implementation that made "two" structural. | ADR-033 |  | Supersedes the two-language assumption in ADR-033. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-042 | Operator Authority — global, flag-granted, outside the tenant model | September 2026 |  |  | Active – extends earlier ADR | High | Built | 1. A second authority, in the same vocabulary. Callers ask for a Permission, never for a flag — ADR-022's rule kept verbatim, for the reason it gives: when operator authority stops being a boolean, the change is to how the set is computed and not to any route. Operator permissions are members of the same closed StrEnum, prefixed OPS_, granted by users.is_staff and by nothing else. ROLE_PERMISSIONS never contains… | Accepted (September 2026). Extends ADR-039, which stands unchanged for everything scoped to a tenant. | ADR-039 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-043 | Payment Adapter Port, Monetisation Still Deferred | September 2026 |  |  | Active | High | Built | Build the payment adapter port only — an interface plus a console implementation that refuses to run, following ADR-017's own precedent for notifications and email. No gateway integration, no Order, Entitlement, or Payout table, and no route calls it. This is not a claim that ADR-025's gate is passed. | Accepted (September 2026). Carries ADR-025's deferral clause forward — it does not declare that clause satisfied. | ADR-025 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-044 | Operator Authority Tiers | September 2026 |  |  | Active – extends earlier ADR | High | Built | 1. A second column, not a second model. users.staff_tier: str ¦ None, closed to STAFF_TIERS = ("support", "admin"). NULL iff is_staff is false — ck_users_staff_tier_pairs_with_flag makes "staff with no tier" and "tiered but not staff" both unrepresentable, the same shape ADR-042 used for tenants.verified_at/verified_by. Still not a role: this is a second global flag beside is_staff, on the same users row, never a… | Accepted (September 2026). Extends ADR-042, which stands unchanged for the question it already answers -- operator authority is global, flag-granted, and not a Membership role. This ADR answers the question ADR-042 deliberately left open and named its own escape hatch for. | ADR-042 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-045 | Gig / Short-Term Work — Design Phase (BL-8.1) | September 2026 |  |  | Superseded in part | Low | Partly built | 1. A new sibling module, api/modules/gig/. Depends on identity (who posted, who worked), geography (district-level proximity, reusing the existing PlaceIndex resolution — no new location-resolution logic), and skills (required standards, compared at concept level via the same Skill.concept_id or Skill.id key scoring.py and courses_closing_gap already use). Does not import marketplace, and nothing in marketplace… | Superseded in part by ADR-046 (September 2026). §1–4 below (the sibling module, the new tables, the second scorer) are withdrawn — the owner determined a gig is a temporary job assignment and should be treated as one, reusing Job/Application instead. §5 (no payment/payout) is untouched and still holds. Kept here in full, not deleted: its reasoning about why a gig looked like a different market was not wrong on its own terms, and a future story revisiting this boundary should read both ADRs. Nothing described below was ever built against this design; BL-8.2 was built against ADR-046 instead. | ADR-046 | ADR-046 | Sections 1-4 (a sibling module for gig work) replaced by ADR-046: a gig is a Job. | ADR-045 header
ADR-046 | Gig Work Reuses `Job` — Supersedes ADR-045 §1–4 (Sprint 37, Epic B8) | September 2026 |  |  | Active – supersedes part of ADR-045 | High | Built | 1. A gig is a Job with employment_type="gig". No new module, no GigListing, no GigListingSkill. Job.district_id (already NOT NULL-enforced in effect by resolve_location), Job.closes_at, Job.positions are exactly ADR-045's "a district, a window, a headcount" — they already existed on Job, unused by permanent vacancies for anything but the closing-date/auto-close feature Sprint 27 built. Two invariants close the… | Accepted (September 2026). Implemented and live-verified in the same sprint. |  |  | Supersedes ADR-045 sections 1-4. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-047 | Provider-Reported Enrolment Surface — Closing the Structural Half of ADR-025's Gate | September 2026 |  |  | Active – extends earlier ADR | High | Built | Add "enrolled" to CourseInterest's status set, provider-settable at the same unverified trust level "contacted" already carries. Add scripts/report_conversion_metrics.py (make monetisation-metrics) to compute click-through and enrolment conversion from columns that already exist — a sibling to make evaluate, which already answers precision@5 and touches no analytics_events row. No new table, no new module, no new… | Accepted (September 2026). Extends ADR-025 and ADR-043. Does not authorise BL-1.3 (billing) on its own. | ADR-025, ADR-043 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-048 | Hire and Train — An Employer May Prompt a Candidate, Never Learn Who They Are First | October 2026 | 27 |  | Active – extends earlier ADR | High | Built | An employer looking at a one-standard-short card may open "Train and hire", see the courses that teach that one standard, and offer to sponsor it. The offer is a row in sponsor_intents (migration 0042), unique per (vacancy, candidate). The candidate receives one in-app notice (sponsor_offer) naming the organisation, the standard and the course, linking to the vacancy. Applying is the act that discloses the… | Accepted (October 2026). Extends ADR-037 (de-identified employer payloads) and the alert sweep's rules (Sprint 27). Introduces no revenue mechanism and no external integration. | ADR-037 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-049 | Career Ladders Are Derived at Read Time From Qualification Data, Not From a Stored Graph | October 2026 |  |  | Active – extends earlier ADR | High | Built | A career ladder is derived at read time from the qualification data, states the evidence for every step, and stores nothing. GET /me/careers (module api/modules/careers/, the career_paths/ ADR-008 reserved, named shorter) lists up to eight roles that build on the person's own. Three modules each own one question: skills.roles_above (which roles build on one), the one scorer through matching.score_against_roles… | Accepted (October 2026). Implements the first slice of ADR-008 (the career path engine) without the inference graph ADR-008 and BL-6.3 assumed. Relaxes BL-6.3's dependency on BL-6.1/6.2 for this slice only. Introduces no revenue mechanism and no external integration. | ADR-008 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-050 | Role Search Ranks Disability-Track Packs One Tier Lower, and They Are Never an Alias Target | October 2026 | 23 |  | Active – extends earlier ADR | High | Built | - A disability-track pack is demoted by one match tier unless the query asks for one (it contains divyang, pwd or disab) or is exactly the pack's title. Implemented as a 1.01 subtraction from the match score, so a disability-track prefix match (3.0) falls just below a general contains match (2.0) and stays above weaker guesses. ROLE_REPRESENTATIVE_ORDER, shared with career ladders, now puts a general pack before… | Accepted (October 2026). Refines the role-search rules in ADR-041's search path and the alias rules written into role_aliases.py since Sprint 23. Introduces no migration and no external integration; scoring, the golden set and make evaluate are untouched. | ADR-041 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-051 | Changing Who Owns an Organisation Is Serialised per Organisation, and Handing It Over Is One Act | October 2026 | 25 |  | Active – extends earlier ADR | High | Built | - Every act that changes who owns an organisation first takes a lock on the tenant row (SELECT ... FOR NO KEY UPDATE, _lock_ownership): role change, removal, leaving, the new handover, and account erasure. Taken before the count and held until the commit. Erasure locks every organisation the account belongs to in ascending id order (lock_ownership_of), the only place more than one is held. - After the lock, the… | Accepted (October 2026). Refines the "last owner" rule of Sprint 25 (ADR-038/039) and adds BL-9.1. One migration (0045, two CHECK widenings). No external integration; scoring is untouched. | ADR-038 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-052 | A Check That Guards an Invariant Takes a Lock; a Cap That Deters Abuse May Stay Advisory | October 2026 |  |  | Active | High | Built | - A check whose result must still be true when the write lands takes SELECT ... FOR UPDATE on the row it read (of= the entity, so a joined relationship cannot make PostgreSQL refuse it) and re-reads under the lock with populate_existing. Applied to applications.service.apply (the existing row) and withdraw, employer_service. set_status, interests.service.register, and provider_service.set_status. - Where there is… | Accepted (October 2026). Generalises ADR-051 from ownership to the candidate-facing write paths, and refines the role-search tiers of ADR-050 (BL-12.14). No migration and no external integration. | ADR-050, ADR-051 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-053 | Dependency Majors Arrive Alone, and a Held Major Carries Its Reason | October 2026 | 20 |  | Active – extends earlier ADR | High | Built | - Minor and patch updates are grouped; a major arrives as its own pull request. Applies to the npm and uv groups. GitHub Actions are not grouped, so each already arrives alone. - TypeScript and ESLint majors are ignored, with the reason written in dependabot.yml and a condition for revisiting each: openapi-typescript accepting TypeScript 7, and eslint-config-next's React plugin running under ESLint 10. They… | Accepted (October 2026). Refines the "Dependabot opens grouped weekly updates" decision of Sprint 20. No migration and no external integration. |  |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-054 | Role Aliases Are Edited by an Operator, the Table Is the Source of Truth, and the Seed Never Overwrites an Operator | October 2026 | 23 |  | Active – replaces a sprint decision | High | Built | - The table is the source of truth. role_aliases gains source (seed ¦ operator), retired_at and created_at; every existing row is seed. The dict only seeds. - The seed never touches an operator's work (sync_seed_aliases): it inserts what is missing, updates a seed row whose target changed, and removes a seed row the dict no longer names. A row with source='operator' — including a retired one — is left exactly as… | Accepted (October 2026). Supersedes the "the dict is the authored source of truth" arrangement of Sprint 23 and Sprint 40. One migration (0046). No external integration; scoring and the golden set are untouched. |  |  | Replaces the Sprint 23 arrangement where the role-alias dict was the source of truth. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-055 | What Erasure Deletes, the Export Shows, and a Guard Keeps Them in Step | October 2026 | 20 |  | Active – extends earlier ADR | High | Built | - The export now carries all four (job_alerts, sponsorship_offers, ratings_received, ratings_given, notices), built by small helpers beside export_account. An empty account exports empty lists, not missing keys. - Nobody else is named. A received rating shows the rating, the comment, the vacancy and the organisation that gave it (who they dealt with, so naming it tells them nothing new) and never author_user_id.… | Accepted (October 2026). Refines the DPDP export and erasure of Sprint 20 (ADR-023 adjacent). No migration and no external integration. | ADR-023 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-056 | Retrieval Ranks Before It Caps, and What It Ranks By Is a Bound, Not a Second Scorer | October 2026 |  |  | Active – extends earlier ADR | High | Built | - Retrieval keeps the K highest upper bounds on the score (api/modules/matching/retrieval.py). The score is coverage plus level, experience and evidence, capped when a mandatory standard is missing. Coverage and the mandatory count come from the database in one aggregation; the other three components are not known without loading the person, so they are taken as full marks (each is at most 1). The cap is applied… | Accepted (October 2026). Refines ADR-007's two-stage matching and leaves ADR-036 and ADR-037 standing. No migration and no external integration. | ADR-007, ADR-036, ADR-037 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-057 | A District's Skill Gap Is Ranked by Shortfall, and a Count of Fewer Than Five Residents Is Never Shown | October 2026 |  |  | Active | High | Built | - Every standard an open vacancy in the district requires is listed, ranked by shortfall. No threshold decides what appears. Demand is the head-count (Job.positions) of the district's open vacancies (open_job()), a standard a vacancy lists twice through two rows of one concept counting once. Supply is the number of distinct residents (CandidateProfile.district_id, where they live, not where they said they would… | Accepted (October 2026). Completes BL-12.7. No migration; read-only, operator-only, beside the programme report (OPS_PROGRAMME_READ, so support and admin tiers, ADR-044). | ADR-044 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-058 | Notifications Are Kept for Ninety Days, an Unopened Notice for a Hundred and Eighty, and a Message Still Owed Never Goes | October 2026 |  |  | Active | High | Built | a worker cron (purge_expired_notifications, 03:15 India time, fifteen minutes after the analytics purge) deletes, by created_at, three classes counted separately in the log: - delivered -- email that is sent, skipped or terminally failed, older than NOTIFICATION_RETENTION_DAYS (default 90, at least 7); - read -- an in-app notice the person opened, older than the same period; - unread -- an in-app notice nobody… | Accepted (October 2026). Closes the item ADR-055 recorded as not done. No migration. | ADR-055 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-059 | Every Route's Audience Is Stated, and a Test Reads It Back From the Route Table | October 2026 |  |  | Active | High | Built | tests/test_authorization_matrix.py builds the list of operations from the OpenAPI schema, so a route added tomorrow is covered the day it exists, and asks four questions of every one: - Anonymous. Every route not named in PUBLIC_ROUTES -- each with its reason -- answers 401. A route that forgot its guard answers 200, 404 or 422 and the failure names it. The list is itself checked: an entry for a route that no… | Accepted (October 2026). A test-only change plus one attribute on require_operator's dependency. |  |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-060 | A Count Is Computed Where the Rows Are, a Question About Many People Is Asked Once, and a Sweep Cannot Stall Behind What It Cannot Do | October 2026 |  | 0047 | Active – extends earlier ADR | High | Built | - A question about many people is asked once (matching/batch.py, profiles_with_serious_match). "Does this candidate have any serious match" needs only the pairs that can reach 60, and the retrieval bound says which: score - 0.5 <= 100 bound (ADR-056), so a pair scoring 60 has a bound of at least 0.595. The database finds each candidate's pairs at or above that, best first, and only those are scored, exactly,… | Accepted (October 2026). Extends ADR-056's scale work to the rest of the product. Migration 0047 (two indexes, no data change). | ADR-056 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-061 | A Public Figure About People Names What It Counts, Leads With the Defensible Number, and a Demonstration Says So | October 2026 | 50.5 |  | Active | High | Built | - Six figures, each with its definition written where it is computed (marketplace/stats.py), and where a broad and a narrow figure differ both are returned and the page names the narrow one underneath, the jobs_posted / jobs_open pattern: - Job seekers: a profile with at least one declared standard (marketplace.skilled_profile(), now the one definition, shared with the employer console). It leads, because a… | Accepted (October 2026). Sprint 50.5. No migration; one new field on an existing public endpoint. |  |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-062 | Journeys Run in a Real Browser, Against the Production Build, and a Check That Cannot Fail Does Not Count | October 2026 | 52 | 0049 | Active | High | Built | - Playwright, Chromium only, on the production build. next build && next start, not next dev: the CSP is looser in development, the service worker registers only in a production build, and sw.js's DENY list is a security boundary nothing else exercises. The API is the real one on its own database, iism_e2e, with ENVIRONMENT=test (the sign-in code is returned and the form prints it). Ports are 8100 and 3100, so… | Accepted (October 2026). Sprint 52. One new dev dependency (@playwright/test, pinned exactly); migration 0049 is separate. |  |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-063 | A Spreadsheet Is Many Writes Through the One Writer, Checked Before It Is Applied, Applied as Drafts, and Published as a Separate Act | October 2026 | 51 | 0048 | Active | High | Built | - A CSV, UTF-8 (a BOM is tolerated), sent as the raw text/csv request body. No multipart, no new dependency (the standard library's csv), and no CSV library shipped to the client: the browser reads the file with file.text() and posts it. XLSX is deferred; Excel exports "CSV UTF-8". The route declares the body in its OpenAPI (openapi_extra), so the generated client types it as a string. - Three acts, each its own… | Accepted (October 2026). Sprint 51. Migration 0048. (ADR-062 is held for Sprint 52's browser-test dependency.) | ADR-062 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-064 | A Published Listing Keeps Its Standards, an Upload Updates Only by Reference and Only the Columns It Carries, and the Browser Sees Every Page | October 2026 | 53 |  | Active – extends earlier ADR | High | Built | - Published implies at least one standard, enforced at every write that can break it. listings.refuse_emptying_a_published is called first thing in update_job and update_course (before any field changes): a published listing saved with no standards is a 422 naming the rule and the way out ("add one, or unpublish it first"). A draft may still be saved with none (unfinished, not live), and unpublishing first… | Accepted (October 2026). Sprint 53. No migration. Extends ADR-062 and ADR-063. | ADR-062, ADR-063 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-065 | The Footer Waits for the Page, a Page Must Not Jump While It Loads, and the Content Security Policy Is Enforced | October 2026 | 54 |  | Active – replaces a sprint decision | High | Built | - The footer is hidden, not removed, while anything on the page is still a placeholder. body:has([data-loading]) footer { visibility: hidden } in globals.css. Every Skeleton carries data-loading; a placeholder that is not a Skeleton must carry the attribute itself. visibility, not display, so the footer keeps its box and appearing moves nothing, and a hidden element is not counted as having shifted. This is one… | Accepted (October 2026). Sprint 54. No migration, no new dependency. Extends ADR-062; supersedes the "ships report-only" decision of Sprint 20. | ADR-062 |  | Replaces Sprint 20's report-only Content-Security-Policy with an enforced one. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-066 | A Code May Be Asked For Again After a Wait, a Credential Is Changed by Proving the New One, and Changing It Ends the Other Sessions | October 2026 | 56 |  | Active – extends earlier ADR | High | Built | - One cooldown, in the one place every code request passes. enforce_otp_rate_limit does SET NX EX first: a second request for the same identifier inside otp_resend_cooldown_seconds (default 30) is a 429 with Retry-After and a sentence saying how long. It is checked before, and does not spend, the 15-minute budget. It is per identifier whether or not an account exists, as the budget already was, so it is not an… | Accepted (October 2026). Sprint 56. No migration. Extends ADR-009, ADR-032 and ADR-038. | ADR-009, ADR-032, ADR-038 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-067 | A Grievance Is a Row With a Deadline, We Never Write to an Address a Stranger Typed, and a Public Form Carries Its Own Limits | October 2026 | 57 | 0050 | Active – extends earlier ADR | High | Built | - A new leaf module, api/modules/grievances/ (one table, grievances). kind is contact, grievance or data_request; status is open, acknowledged, resolved or dismissed; a reference (GRV- and six unambiguous characters, unique, drawn again inside a savepoint on a collision) is what the sender keeps. CHECKs hold the rules the service holds: a body of 10 to 4,000 characters, somebody to reach (user_id or reply_to), a… | Accepted (October 2026). Sprint 57 (BL-14.3). Migration 0050. Extends ADR-023, ADR-042 and ADR-044. | ADR-023, ADR-042, ADR-044 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-068 | A Recommendation Says Whether You Can Act on It: a Course Has a Place, an Intake and Seats, and Attendability Orders Suggestions Without Touching the Score | October 2026 | 58 | 0051 | Active – extends earlier ADR | High | Built | - Six nullable columns on courses: location_state, location_district (free text), state_id, district_id (SET NULL foreign keys, resolved on write with the one geography.resolve_location, before anything changes, the Sprint 55 refuse-first rule), starts_on (a calendar date; null is a rolling or unstated intake) and seats (CHECK >= 1). Nothing is backfilled: a course published before this has no stated place, and a… | Accepted (October 2026). Sprint 58 (BL-14.5, BL-14.6). Migration 0051. Extends ADR-036, ADR-037 and ADR-047. | ADR-036, ADR-037, ADR-047 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-069 | A Takedown Is a Draft With a Stamp, Not a Third Status; Reports Are Grouped by Listing and Decided by a Human, Never by a Count | October 2026 | 59 | 0052 | Active – extends earlier ADR | High | Built | - A takedown is status="draft" plus taken_down_at and takedown_reason (set together, a CHECK on each table), not a third status. A draft is excluded by every public query for free. A vacancy is also closed with the new reason taken_down (the one close reason an owner cannot claim, as expired is the worker's), so it stops counting as open and its live applicants are told through the notice a closed vacancy already… | Accepted (October 2026). Sprint 59 (BL-14.4). Migration 0052. Extends ADR-042, ADR-044 and ADR-067. | ADR-042, ADR-044, ADR-067 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-070 | A Message With a Status Is Read From the Application and Never Copied Into the Outbox; Notes Are the Employer's and in the Person's Export; One Serialiser Feeds the List and the Spreadsheet | October 2026 | 60 | 0053 | Active – extends earlier ADR | High | Built | - The message is stored on the application and never in the outbox. status_message (500 characters, a CHECK as well as the schema) is replaced when one is given, cleared when the status really changes and none is given, and left alone when the status is unchanged and none is given (a second click on "Shortlist" must not erase an interview time). The notice carries has_message: true and the path; the words are… | Accepted (October 2026). Sprint 60 (BL-14.7 to BL-14.9). Migration 0053. Extends ADR-006, ADR-023, ADR-037 and ADR-055. | ADR-006, ADR-023, ADR-037, ADR-055 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-071 | An Operator Enrols an Agency's File From the Back Office, and the Consent It Stamps Is an Attested Claim Recorded Against a Named Operator | October 2026 | 61 | 0054 | Active – extends earlier ADR | High | Built | - One engine, in operations/enrolment.py, called by both the back office and the script. It is a sibling of marketplace/bulk.py (ADR-026, ADR-063: bulk.run is hard-wired to a tenant and to vacancies and courses) and reuses its file reading. To make that possible without moving a 1,482-line module, parse_file was split into a kind-free parse_records(text, columns=, required=, max_rows=) that it now calls, and the… | Accepted (October 2026). Sprint 61 (BL-14.10). Migration 0054. Extends ADR-042, ADR-044, ADR-055 and ADR-063. | ADR-042, ADR-044, ADR-055, ADR-063 |  |  | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-072 | The Mobile App Is a Second Client of the Same API, in the Same Repository; Released Operations Are Additive-Only and an Old Build Is Told to Update | October 2026 | 62 |  | Active – extends earlier ADR | High | Built | - No separate branch and no rebaseline. The backend is the contract and stays one. The app lives in a new top-level mobile/ directory of this repository; web/ and api/ are not moved. Work is on short-lived mobile-N branches merged to main, one per sprint, like Sprints 56 to 61; a store release is tagged mobile-vX.Y.Z so a build can be reproduced and a hotfix cut from the tag. - v1 is candidate-only. The PRD… | Accepted (October 2026). Sprint 62 (BL-15.1, BL-15.7). Extends ADR-002, ADR-016 and ADR-029. No migration. | ADR-002, ADR-016, ADR-029 |  | Mobile programme (Sprints 62-65). Compiled, tested and browser-run; never run on a device. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-073 | The Phone Persists Public Data Only, by an Allow-List of Query Keys, and Formats Numbers and Dates Without `Intl` | October 2026 | 63 |  | Active – extends earlier ADR | High | Built | - What is persisted is an allow-list, not a deny-list. Every visitor query is keyed ["public", <locale>, kind, filter] (mobile/src/lib/queries.ts). persist.ts's isPublicKey accepts only a first key element of "public"; the persister keeps a query only if it is public and has data (query.state.data !== undefined). shouldDehydrateMutation is () => false. A personal query (["me"], ["profile"], ["matches"], anything… | Accepted (October 2026). Sprint 63 (BL-15.2, M2 of the mobile programme). Extends ADR-072. No migration, no API change beyond ten read operations added to the released surface. | ADR-072 |  | Mobile programme (Sprints 62-65). Compiled, tested and browser-run; never run on a device. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-074 | The Phone Holds a Person's Data in Memory Only and Drops It at Sign-Out; Applying and Registering Interest Are the Consent Moment and Say So; the Score Is Displayed, Never Derived | October 2026 | 64 |  | Active – extends earlier ADR | High | Built | - Everything about a person is keyed ["me", ...] (mobile/src/core/me-keys.ts) and is never persisted: ADR-073's allow-list keeps only keys starting "public", so a personal query cannot reach the disk by being added. A test names each key and refuses it; another fails if a personal query is built anywhere but lib/me-queries.ts. - Signing out drops all of it, whole. forgetEverything clears the query client (not… | Accepted (October 2026). Sprint 64 (BL-15.3, M3 of the mobile programme). Extends ADR-037, ADR-070 and ADR-073. No migration, no backend change; sixteen operations are added to the released surface (33 in all). | ADR-037, ADR-070, ADR-073 |  | Mobile programme (Sprints 62-65). Compiled, tested and browser-run; never run on a device. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-075 | A Push Is Something the Worker Does for an In-App Notice, Says Nothing From the Notice, and Reaches a Person Only Through a Phone They Registered | October 2026 | 65 | 0055 | Active – extends earlier ADR | High | Built | - A phone is a row (device_tokens): the token, the platform, the language, two times. A token is unique and belongs to one person at a time: registering one another account holds moves it, in one atomic upsert, because on a shared phone the last person to sign in is the one the next push is for. A person holds at most ten; unregistering is idempotent, deletes only the caller's own, and answers the same whether… | Accepted (October 2026). Sprint 65 (BL-15.6, M4 of the mobile programme). Extends ADR-006, ADR-017, ADR-023 and ADR-070. Migration 0055. | ADR-006, ADR-017, ADR-023, ADR-070 |  | Mobile programme (Sprints 62-65). Compiled, tested and browser-run; never run on a device. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-076 | Store Reviewers Sign In With a Fixed Code on Named Phones, Behind an Explicit Production Switch, and Only to a Demonstration Account | October 2026 | 65 |  | Active – extends earlier ADR | High | Built | - A named exception, off by default. REVIEWER_LOGIN_ENABLED (false), REVIEWER_PHONES (at most five, each a phone), REVIEWER_CODE (exactly otp_length digits, from the environment, never the repository). For a listed phone request_otp stores the configured code and sends no SMS; every other number takes the normal path unchanged. The request is otherwise identical: same rate limit and cooldown, same answer, so it… | Accepted (October 2026). Sprint 65 (BL-15.8, M4 of the mobile programme). Extends ADR-032, ADR-038 and ADR-066. No migration. | ADR-032, ADR-038, ADR-066 |  | Mobile programme (Sprints 62-65). Compiled, tested and browser-run; never run on a device. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md
ADR-077 | A Release Build Fails Closed, What Is Still the Owner's Is Counted Rather Than Hidden, and the Stores' Answers Are Checked Against the Data They Describe | October 2026 | 66 |  | Active – extends earlier ADR | High | Built | - A release build refuses to start on a development origin. core/release.ts (configProblems, pure) is fed the build's own EXPO_PUBLIC_API_BASE_URL and EXPO_PUBLIC_WEB_BASE_URL and !__DEV__; a missing origin, an http:// one or a local one (localhost, 127., 10.0.2.2, ::1, .localhost) makes the root layout render Misconfigured instead of the router. The person is told in plain words to reinstall; the reason goes to… | Accepted (October 2026). Sprint 66 (BL-15.5, M5 of the mobile programme). Extends ADR-072 and ADR-076. No migration, no API change (the contract is untouched). | ADR-072, ADR-076 |  | This sprint (66). Mobile release: fail-closed config, owner items counted, store answers checked against the data export. Not run on a device or EAS build. | ADR header and sprint record in CLAUDE.md / projectContextForMe.md

## Stale headers
ADR | Header says | What is actually true | Kind | Suggested one-line header edit
ADR-019 Observability Strategy | Accepted | Tooling half replaced by ADR-040 (structured JSON logs to stdout). The destination (OpenTelemetry, Prometheus, Grafana) remains deferred and unbuilt. | Header silent about a later ADR or event | Superseded in part by ADR-040 (tooling); destination deferred.
ADR-032 Primary Credential by Actor Type | Accepted (September 2026) | The organisation half (email OTP, password-free) is replaced by ADR-038; the credential-follows-actor rule still governs sign-up. | Header silent about a later ADR or event | Superseded in part by ADR-038 (organisation half).
ADR-033 Language Scope at Launch | Accepted (September 2026) | The two-language assumption is replaced by ADR-041 (a language is a messages file and rows). Hindi and English remain the launch pair; Malay is hidden from the switcher, not removed. | Header silent about a later ADR or event | Superseded in part by ADR-041 (two-language assumption).
ADR-037 The Employer Console as a Labelled Demonstration | Accepted (September 2026) | The rule that no employer-facing payload identifies a candidate stands and is tested. The 'unauthenticated demonstration' framing no longer describes the product: the authenticated employer console shipped to production in Sprint 12 (ADR-038); only the unauthenticated demo console is local-only. | Header silent about a later ADR or event | Superseded in part: console is authenticated and ships to production (ADR-038); de-identification rule stands.
ADR-005 AI Strategy | Accepted | No LLM call exists anywhere; the intelligence/ module has an ADR and no code. The direction stands: ADR-036 keeps every decision deterministic and lets a model only explain. | Decision stands; header says nothing of implementation lag | Accepted; not built.
ADR-011 Identity Model | Accepted | UUID primary key built. Optional Aadhaar verification is not built and nothing collects Aadhaar data. | Decision stands; header says nothing of implementation lag | Accepted; Aadhaar verification not built.
ADR-013 Embedding Strategy | Accepted | pgvector storage and a 384-dimension port are built (ADR-031). The mandated sentence-transformers model is not switched on: HashingEmbeddingProvider is an honest placeholder and BL-5.3 is not started. | Decision stands; header says nothing of implementation lag | Accepted; placeholder embedder in use (BL-5.3).
ADR-018 AI Model Strategy | Accepted | No external LLM is integrated. The adapter pattern it depends on exists (ADR-017, ADR-031). | Decision stands; header says nothing of implementation lag | Accepted; not built.
ADR-023 Data Privacy & Compliance | Accepted | Consent record, DPDP export, erasure, the redaction filter and retention are built. The encryption path for Aadhaar, resumes and assessment results is not, so that data is deliberately not collected. | Decision stands; header says nothing of implementation lag | Accepted; encryption path unbuilt.
ADR-025 Monetization Model | Accepted (September 2026) | Monetisation (BL-1.3) is a standing not-started: the owner chose to wait for real traffic. ADR-043 and ADR-047 carry the deferral. | Decision stands; header says nothing of implementation lag | Accepted; deferred by owner.
ADR-028 Cloud Platform and Deployment Topology | Accepted (September 2026) | Nothing is deployed anywhere; deployment is deferred by the owner and is now on the mobile launch's critical path. Still the intended topology. | Decision stands; header says nothing of implementation lag | Accepted; deferred by owner, nothing deployed.

## By sprint
Sprint | ADRs | Decisions | Migration
Sprint 20 | ADR-053, ADR-055 | Dependency Majors Arrive Alone, and a Held Major Carries Its Reason; What Erasure Deletes, the Export Shows, and a Guard Keeps Them in Step
Sprint 23 | ADR-050, ADR-054 | Role Search Ranks Disability-Track Packs One Tier Lower, and They Are Never an Alias Target; Role Aliases Are Edited by an Operator, the Table Is the Source of Truth, and the Seed Never Overwrites an Operator
Sprint 25 | ADR-051 | Changing Who Owns an Organisation Is Serialised per Organisation, and Handing It Over Is One Act
Sprint 27 | ADR-048 | Hire and Train — An Employer May Prompt a Candidate, Never Learn Who They Are First
Sprint 42 | ADR-008 | Career Path Engine
Sprint 50.5 | ADR-061 | A Public Figure About People Names What It Counts, Leads With the Defensible Number, and a Demonstration Says So
Sprint 51 | ADR-063 | A Spreadsheet Is Many Writes Through the One Writer, Checked Before It Is Applied, Applied as Drafts, and Published as a Separate Act | 0048
Sprint 52 | ADR-062 | Journeys Run in a Real Browser, Against the Production Build, and a Check That Cannot Fail Does Not Count | 0049
Sprint 53 | ADR-064 | A Published Listing Keeps Its Standards, an Upload Updates Only by Reference and Only the Columns It Carries, and the Browser Sees Every Page
Sprint 54 | ADR-065 | The Footer Waits for the Page, a Page Must Not Jump While It Loads, and the Content Security Policy Is Enforced
Sprint 56 | ADR-066 | A Code May Be Asked For Again After a Wait, a Credential Is Changed by Proving the New One, and Changing It Ends the Other Sessions
Sprint 57 | ADR-067 | A Grievance Is a Row With a Deadline, We Never Write to an Address a Stranger Typed, and a Public Form Carries Its Own Limits | 0050
Sprint 58 | ADR-068 | A Recommendation Says Whether You Can Act on It: a Course Has a Place, an Intake and Seats, and Attendability Orders Suggestions Without Touching the Score | 0051
Sprint 59 | ADR-069 | A Takedown Is a Draft With a Stamp, Not a Third Status; Reports Are Grouped by Listing and Decided by a Human, Never by a Count | 0052
Sprint 60 | ADR-070 | A Message With a Status Is Read From the Application and Never Copied Into the Outbox; Notes Are the Employer's and in the Person's Export; One Serialiser Feeds the List and the Spreadsheet | 0053
Sprint 61 | ADR-071 | An Operator Enrols an Agency's File From the Back Office, and the Consent It Stamps Is an Attested Claim Recorded Against a Named Operator | 0054
Sprint 62 | ADR-072 | The Mobile App Is a Second Client of the Same API, in the Same Repository; Released Operations Are Additive-Only and an Old Build Is Told to Update
Sprint 63 | ADR-073 | The Phone Persists Public Data Only, by an Allow-List of Query Keys, and Formats Numbers and Dates Without `Intl`
Sprint 64 | ADR-074 | The Phone Holds a Person's Data in Memory Only and Drops It at Sign-Out; Applying and Registering Interest Are the Consent Moment and Say So; the Score Is Displayed, Never Derived
Sprint 65 | ADR-075, ADR-076 | A Push Is Something the Worker Does for an In-App Notice, Says Nothing From the Notice, and Reaches a Person Only Through a Phone They Registered; Store Reviewers Sign In With a Fixed Code on Named Phones, Behind an Explicit Production Switch, and Only to a Demonstration Account | 0055
Sprint 66 | ADR-077 | A Release Build Fails Closed, What Is Still the Owner's Is Counted Rather Than Hidden, and the Stores' Answers Are Checked Against the Data They Describe