## About
IISM: what has been delivered through Sprint 92 (as at 2026-10-22)
Prepared as the Product Owner's view of completed work: one row per sprint on 'Sprints', one row per completed backlog story on 'Completed stories'.
94 sprint records (Sprints 1 to 92, with 22.5 and 50.5, and 30 and 31 shown separately). 87 backlog stories are Done, 5 Partly done and 4 Closed without being built (Epic B21's palette stories: the Product Owner kept the blue).
Read with care: the backlog's status table groups some work (for example 'BL-2.1 to 2.4' is one row), so the story count is rows, not individual tickets. Sprints 1 to 7, 26, 27, 30, 31 and 39 are summarised from the project's context notes and the git history, not from a full sprint record; Sprints 28 onward come from the sprint records in CLAUDE.md and projectContextForMe.md.
Not delivered and deliberately deferred by the Product Owner: monetisation and billing (BL-1.3, waiting on real traffic), every live external integration (SMS, payments, assessment partners, Aadhaar), deployment, SEO. The phone app has been compiled, tested and run in a browser but never on a device.
Next, as planned on 2026-10-22: Sprints 93 to 101 (foundations; the dual-role training organisation; centres; delivery authorisations; batches; nearby batches).

## Sprints
Sprint | Sprint focus | Sprint summary | Done on | ADRs | Migration | Stories / epic
1 | Walking skeleton | Docker Compose, async FastAPI, Alembic with pgvector, an ARQ worker with a heartbeat health probe, a bilingual Next.js PWA, a generated TypeScript client, testcontainers-backed tests and CI. Visible result: the System Status page in English and Hindi. | Aug 2026 |  |  | Foundations
2 | Skill taxonomy | `Skill` and `SkillAlias`: 52 bilingual skills and 149 aliases across Healthcare, Retail and core skills. Search resolves English, Devanagari and Latin-script transliteration in one query, with a trigram fallback for typos. `/skills` pages live in both languages. | Aug 2026 |  |  | Taxonomy
3 | Marketplace | Jobs and courses with the skills they need or teach (`JobSkill.importance` and `is_mandatory`, `CourseSkill.level_taught`), 8 tenants, 20 jobs and 20 courses seeded, `/jobs` and `/courses` with filters and detail pages. | Aug 2026 |  |  | Marketplace
4 | Identity and candidate profile | Passwordless phone sign-in (OTP stored hashed, rate-limited, five guesses), `User`/`Tenant`/`Membership`, phone numbers normalised to +91, a candidate profile and skills; `/signin` and `/profile` live. | Aug-Sep 2026 |  |  | Identity
5 | Rich candidate profile | Personal details, job preferences and six repeating collections (experience, education, certifications, languages, preferred roles and locations), a guided wizard for a first visit, a sectioned editor after, and a weighted completeness meter. | Sep 2026 |  |  | Candidate profile
6 | NSQF master data (built, then rolled back) | Projected the national corpus from MongoDB into PostgreSQL, audited the source data and found it did not hold what was assumed; rolled back and the findings recorded in docs/nsqf-source-data-findings.md. The audit is what made Sprint 8 correct. | 2026-09-04 | ADR-034, ADR-035 | (rolled back) | NSQF
7 | Taxonomy usable at scale | Made browsing and searching a 21,355-skill taxonomy usable (facets, paging, search); folded into the same rolled-back migration and redone in Sprint 8. Inferred from the repository history; not separately written up. | 2026-09-04 |  | (rolled back) | NSQF
8 | Complete NSQF migration | Migrated the full corpus against the complete master data: 36 states, 766 districts, 21,303 standards, 4,424 qualification packs, ~614k rows of content. Owning body from the code prefix, location foreign keys beside free text, content keyed on parent and ordinal. Idempotent `make import-nsqf` in about 90 seconds. | 2026-09-05 | ADR-034, ADR-035 |  | NSQF corpus
9 | Connect the graph | The national taxonomy becomes the operational vocabulary: every job, course and candidate skill points at a real standard; `skill_concepts` groups the same standard across rows; the 52 curated skills retired (hidden, page still resolves). | 2026-09-06 |  |  | Taxonomy
10 | Matching and the gap | Deterministic, pure scoring (`scoring.py`): a missing mandatory standard caps a score at 45, zero matched is zero; `/matches` shows ranked jobs, the gap by standard, the courses that close it and how to qualify. The golden-set harness (`make evaluate`) is born. | 2026-09-06 | ADR-036 |  | Matching
11 | Make it sellable | A component library on Radix, live counts on the landing page, the employer console ranking candidates through the same scorer in reverse, an installable PWA with a deny-listed service worker, charts that render the scorer's own fields, and twenty seeded candidates. | 2026-09-07 | ADR-037 |  | Employer console, PWA
12 | One identity, many roles | Organisation registration by email code, an employer posts a vacancy against real standards and sees ranked candidates, one `User` with many `Membership` rows, permission-based authorisation (`require()`), 404 not 403 for a stranger. | 2026-09-07 | ADR-038, ADR-039 |  | Multi-tenancy
13 | Multi-tenancy you can see | A header context switcher, creating an organisation without leaving the account, linking a second credential, editing the organisation profile, operator-verified badge (`is_verified`) with `require_operator()`; a personal workspace is not an organisation. | 2026-09-07 | ADR-042 |  | Multi-tenancy, back office
14 | Three ways in, one way back | A training provider can finally register and publish courses (`course_publishing.py`), sign-in is one door for either credential, the header and workspace follow `tenant_type`, and a provider no longer sees an employer's heading. | 2026-09-08 |  |  | Providers
15 | Consolidation | No new surface: four sprints pushed, dead code removed, documents made to agree with the code; `record()` found to raise (fixed), `require()` made to ask permission and tenant type together, closed unions held by `test_enumerations.py`. | 2026-09-09 |  | 0017 | Hardening
16 | Who is this for | The homepage names the three roles (job seeker, employer, provider) with a chooser; a hero fold budget measured for Hindi at 360x640. | 2026-09-10 |  |  | Homepage
17 | Logging you can run a customer on | One structured JSON stream, a redaction filter in the shared processor tail that cannot be bypassed, request id, user id and tenant id on every line, route templates rather than paths, ARQ lines pinned. | 2026-09-10 | ADR-040 |  | Observability
18 | One identity, honestly | `/auth/org/register` never mints a second account for a signed-in caller; surfaces branch on membership; what a sign-in reveals it reveals on verify; landing in one pure function; the web gets a Vitest runner. | 2026-09-11 |  |  | Identity
19 | Every door opens onto all three | `/signup/[type]` carries its own type switch (Find work, Hire, Offer training) as plain links; the form is keyed by type so state does not leak between kinds. | 2026-09-11 |  |  | Sign-up
20 | Safe to deploy | Consent as a server-side record, privacy export and erasure, security headers, body limit and rate limits as pure ASGI middleware, a 15-second statement timeout, encrypted backups and a restore drill, CI from the lockfile, a first-load JS budget. | 2026-09-11 |  | 0018 | NFRs
21 | The loop closes | A candidate applies, withdraws and saves; an employer sees who applied with contact details: the product's one deliberate disclosure, recorded as `contact_shared_at`. `candidate_card()` is the only de-identified payload; a 24-hour application cap. | 2026-09-17 |  | 0020 | Apply and inbox
22 | Many languages, and something arrives | Language moved out of column pairs into `content_translations`; the API resolves language from Accept-Language, a locale and the account; a Malay skeleton proves a third language; a notification outbox (queued, never sent inline). | 2026-09-17 | ADR-041 | 0022 | Localisation, notifications
22.5 | Demo readiness | Every seeded organisation gets an owner account, all five employers an inbox (sixteen applications), fifty courses chosen so every mandatory standard is taught; a missing message key now fails a test. | 2026-09-17 |  |  | Demonstration data
23 | Say what you do, and we'll name the standards | Role search from the corpus (a job title to its qualification's standards), aliases like "ward boy", a ticked suggestion is `self_declared`, bulk add is all-or-nothing, profile location resolves on write, the homepage search answers a job title with jobs. | 2026-09-18 |  | 0024 | Role search
24 | Somebody is interested | A learner registers interest in a course; the provider sees who (the second deliberate disclosure); `interests/` is a sibling of `applications/` with no scoring; `course_recommended` becomes attributable. | 2026-09-21 |  | 0025 | Course interest
25 | An organisation that outlives its owner | Invitations (a row, not a pending membership), team roles, the last-owner rule, an invited stranger can create an account, revoking an invitation stops its mail; sole-owner deletion no longer destroys the organisation. | 2026-09-22 |  |  | Team management
26 | A surface you would show somebody | Typography self-hosted, 305 hard-coded colours replaced by semantic tokens and a test, the dialog bug traced to a containing block, a header with fewer controls; organisations per account uncapped with a duplicate-name refusal and a 24-hour creation cap. | Sep 2026 |  |  | Design system
27 | A vacancy that ends, and alerts that reach people | Closing is not unpublishing (`closed_at`, `open_job()`); `positions` makes "hired" mean something; a worker closes expired vacancies and sweeps job alerts (told once, ever; caps; opt-out). | Sep 2026 |  | 0027 | Vacancy lifecycle, alerts
28 | Clear the decks | Geography resolved correctly (`PlaceIndex`: a district name is not unique), operator authority (`is_verified` finally has a writer), and the fixes the audit queued. | 2026-09-23 |  |  | Hardening
29 | A back office you can see, and a matcher you can defend | The golden set grows to 34 pairs, 7 orderings and 16 course expectations (labels derived from inputs, never from the scorer); the back office is visible. | 2026-09-23 |  |  | Back office, evaluation
30 | The audit | A whole-product audit of the code, security and tests. | 2026-09-24 |  |  | Audit
31 | Acting on the audit | The audit's findings fixed: silent-failure sweep (every write reports its failure), scope ledger. | 2026-09-24 |  |  | Audit
32 | Every handler delegates | Seventeen handlers that held business logic moved into services and a test (`test_route_delegation.py`) keeps the number at zero. | 2026-09-24 |  |  | Architecture
33 | A management-facing MVP push | Thin-slice government-agency and external-system actors, course-to-role alignment, configurable match weights, the `course_dismissed` signal, market-wide scarce skills for providers. | 2026-09-26 |  |  | BL-2.1 to 2.4; actor breadth
34 | Payments, decided | ADR-043: a payment adapter port (the console implementation refuses unconditionally: nothing calls it yet). Monetisation stays gated. | 2026-09-26 | ADR-043 |  | BL-1.1, BL-1.2
35 | Verified evidence | An assessment-provider adapter and webhook writing `source='assessed'`; an operator-verified `certified` path from a candidate's certification, so no `SKILL_SOURCES` value lacks a writer. | 2026-09-26 |  |  | BL-3.1, BL-3.2
36 | Semantic similarity, and the skill graph's foundation | An embeddings adapter and a bounded additive semantic term in `score_match`, a worker cron that fills embeddings and invalidation on skill writes; `SkillRelation` foundation. | 2026-09-27 | ADR-013, ADR-031 |  | BL-5.1, BL-5.2, BL-6.1
37 | Tiered operator authority, then gig work | Support and admin tiers (`staff_tier`), then gig work as a `Job` (`gig` employment type, completed and no-show applications, two-sided ratings) with no change to matching. | 2026-09-28 | ADR-044, ADR-045, ADR-046 |  | BL-7.3, BL-8.1, BL-8.2
38 | Closing ADR-025's structural gate | An `enrolled` status providers can set, and `make monetisation-metrics` to read click-through and enrolment conversion. Monetisation not authorised: volume is the gate. | 2026-09-29 | ADR-047 | 0038 | Monetisation evidence
39 | Actor dashboards | Per-actor dashboards (Epic B10). | Sep-Oct 2026 |  |  | Epic B10
40 | Dashboard visualisation and a cross-sector fix | Chart primitives and drilldowns on all five dashboards (hand-rolled SVG), `role_aliases` as a table, word-synonym expansion, a coverage-tapered mandatory-gap cap, and landing it on main. | 2026-10-02 |  |  | Epic B11
41 | Finish the half-built, then two differentiators | Gig completion and ratings get screens, `enrolled` and learner notice, a certification linked to a standard, seven hardening fixes; "Why not me" for a rejected candidate and "Hire and train" sponsorship offers. | 2026-10-03 | ADR-048 |  | Differentiators
42 | Career ladders | `/career-paths`: the roles that build on yours and what it would take, derived from qualification data with the evidence shown, stored nowhere; measured honestly (38% of roles have a step). | 2026-10-03 | ADR-049 |  | Careers
43 | Role search you can trust | A disability-track pack can no longer lead a general one, half-typed aliases beat prefixes, multi-word queries work; a rejected application cannot be withdrawn and reapplied; an organisation is emailed when its verified badge flips. | 2026-10-04 | ADR-050 | 0044 | BL-12.6, BL-9.2
44 | Hand an organisation over in one act | Transfer of ownership, and the race under it fixed: every ownership change takes a lock and re-checks the caller afterwards (reproduced an organisation with no owner). | 2026-10-04 | ADR-051 | 0045 | BL-9.1
45 | The same blind spot on the common paths | Double-tap on Apply, register interest or save is a 409 not a 500; withdrawing at the instant an employer decides no longer loses an update; abbreviations in role search. | 2026-10-04 | ADR-052 |  | BL-12.14
46 | Dependency triage, and the last race | Five Dependabot PRs unblocked (vitest 5 and jsdom 30 adopted; TypeScript 7 and ESLint 10 held with reasons); slug races on vacancy, course and organisation creation closed with `add_with_unique_slug`. | 2026-10-04 | ADR-053 |  | Dependencies
47 | An operator screen for role aliases | Aliases move to the table as the source of truth; admin-tier operators add and retire them on `/admin`, each change audited. | 2026-10-04 | ADR-054 | 0046 | Role aliases
48 | What erasure deletes, the export shows | The data export now shows alerts, ratings, sponsorship offers and notices (none had been exported); a guard fails on the next table that is not. | 2026-10-04 | ADR-055 |  | DPDP
49 | Matching you can trust at volume | A scale harness found the shortlist returned 2.9 and 1.2 of a true top 20; retrieval now ranks by an upper bound before capping (20 of 20), the district skill-gap view, notification retention, an authorization matrix. | 2026-10-05 | ADR-056 to ADR-059 |  | BL-12.7
50 | Scale the rest | The programme report asks one batch question (22 minutes to 17.6 seconds for 10,000), the employer overview counts in the database, JIT off, embedding sweeps no longer stall. | 2026-10-05 | ADR-060 | 0047 | Scale
50.5 | Show the work done on the homepage | Who is here and what has been done (job seekers, employers, providers, applications, hires, districts), each defined where computed, with a footnote for demonstration data. | 2026-10-05 | ADR-061 |  | Homepage
51 | Bulk upload of vacancies and courses | A spreadsheet is checked, created as drafts, then published as a separate act; a `job_role` expands to its standards; daily caps of 100 and 500; re-uploading creates only what is new. | 2026-10-05 | ADR-063 | 0048 | Bulk upload
52 | Journeys in a real browser | Six Playwright journeys run in CI and every page is checked for console errors, failed requests, CSP violations and contrast in both themes; five real defects found and fixed. | 2026-10-08 | ADR-062 | 0049 | E2E
53 | Every page, an invariant, and the update half of bulk upload | A sweep of about 45 routes in both languages; a published listing can no longer be saved with no standards; bulk upload can update by `external_ref`. | 2026-10-09 | ADR-064 |  | Quality
54 | Pages that do not jump, and a policy that blocks | The footer was the cause of layout shift (0.205 to under 0.1 by one CSS rule); the CSP is now enforced in a production build. | 2026-10-12 | ADR-065 |  | Performance, security
55 | The code review's fixes | `nan` and `inf` no longer turn an upload into a 500, a refused update is no longer saved, a lost race is no longer a 500, check and apply agree about gigs; 20 new tests. | 2026-10-12 |  |  | Review fixes
56 | Never locked out | A code can be asked for again after a cooldown (one place every request passes), and a sign-in credential can be added, changed by proving the new one, or removed while another remains; linking no longer silently overwrites. | 2026-10-13 | ADR-066 |  | Sign-in
57 | A way to complain | `/contact` and `/grievance` become real, with a queue, overdue marks against the page's own promises (24 hours, 15 days), a budget and a honeypot, no relay to a stranger's address. | 2026-10-13 | ADR-067 | 0050 | BL-14.3
58 | Courses you can attend | A course has a place, an intake and seats (seats left derived, never a counter); suggested courses ordered by whether the person can take them, labelled and never hidden; a per-request budget. | 2026-10-13 | ADR-068 | 0051 | Course attendance
59 | A marketplace you can trust | A signed-in person can report a vacancy or course; operators see reports grouped by listing, dismiss them (support) or take a listing down with an emailed reason (admin); takedown is a draft plus a stamp. | 2026-10-13 | ADR-069 | 0052 | BL-14.4
60 | Hiring that finishes | An employer sends a message with a status change and keeps private notes, downloads applicants as a formula-safe spreadsheet; a candidate sees the message, an unread count and a `/notifications` page. | 2026-10-13 | ADR-070 | 0053 | Hiring workflow
61 | A pilot with an agency | An admin operator enrols an agency's file from `/admin`: check, preview, attest the notice was read out, enrol; consent recorded with who, when and which notice version. | 2026-10-14 | ADR-071 | 0054 | BL-14.10
62 | Mobile M1: foundations | An Expo/React Native app in this repository (candidate-only for v1): the 426 update gate, an additive-only API contract check, generated client, messages and colours; compiled and tested, never run on a device. | 2026-10-14 | ADR-072 |  | BL-15.1, BL-15.7
63 | Mobile M2: browse on the phone | A visitor browses jobs, courses and standards, searches and switches language without signing in; a public-only offline cache. | 2026-10-14 | ADR-073 |  | BL-15.2
64 | Mobile M3: the candidate's own side | Sign-in, role picker, ranked matches with the gap and the courses, apply, withdraw, save, register interest, applications; person data in memory only and dropped at sign-out. | 2026-10-15 | ADR-074 |  | BL-15.3
65 | Mobile M4: updates, push, links, account, reviewers | Updates with an unread count, push with fixed words, `iism://` links from one table, export and delete account, contact and report, and a reviewer login behind a production switch. | 2026-10-15 | ADR-075, ADR-076 | 0055 | BL-15.4, 15.6, 15.8
66 | Mobile M5: store readiness | A release build refuses to start on a missing or cleartext origin, `eas.json`, `make check-release` (counts what is still the owner's), a size ceiling, accessibility props, listing and runbook documents checked by tests. | 2026-10-15 | ADR-077 |  | BL-15.5
67 | Mobile M6: candidate parity | The six profile history sections, "why not me", career paths, the course budget and the remaining profile fields on the phone; date of birth and gender stay web-only. | 2026-10-15 | ADR-078 |  | BL-15.9 to 15.11
68 | A whole-product UI review | 29 findings with evidence, a design-system plan and a recommended order (docs/design/); three silent caps found; Epic B16. | 2026-10-15 |  |  | Epic B16
69 | Scannable jobs | Job cards that say what, who, where, how much a month and by when; paging with the server's total; a catalogue-true state filter; an apply bar on the thumb; nothing under 12 px; true operator queue sizes. | 2026-10-16 | ADR-079 |  | BL-16.1
70 | A candidate's first minute | A homepage that leads with search and example jobs in the seeker's words, a matches page that opens on matches, every match explained in a sentence built from the scorer's own lists, a signed-in phone home. | 2026-10-16 | ADR-080 |  | BL-16.2
71 | Role search you can trust (coverage) | Role-alias coverage from 114 forms on 41 roles to 307 on 88, measured by `make evaluate-roles` against titles written before the aliases (hold-out reported separately); the reviewer's workbook. | 2026-10-16 | ADR-081 |  | BL-12.12
72 | A DPDP readiness slice | Withdrawing consent as a pause without deleting the account, a changed notice that asks, an 18-and-over gate, a privacy notice rewritten because it was wrong, a breach runbook. | 2026-10-17 | ADR-082 | 0056 | DPDP
73 | The hiring side's design pass | The back office keeps three queues open and folds four reference panels (40 to 28 screens, 181 small targets to 0), one primary action per row, pool bars that say what amber means. | 2026-10-17 | ADR-083 |  | UI-14, 15, 16, 26
74 | Candidate depth | A vacancy says when it was posted (`published_at`, NULL when nobody knows) and the career page remembers the role you confirm. | 2026-10-18 | ADR-084 | 0057 | BL-6.5
75 | Courses that count toward a qualification | A provider links a course to a qualification (stated by the provider, never a sort or filter), newest-first vacancies, and a bulk-update bug that would have cleared every link. | 2026-10-17 | ADR-085 |  | BL-12.8
76 | Epic B19 begins: competitor review and a direction | Eight competitor sites reviewed live; a visual direction signed off (a refresh within the blue, a grey page with white cards, a named type scale). | 2026-10-17 |  |  | BL-19.1, 19.2
77 | Foundations: the look chosen in one place | Colour ramps and semantic tokens, a named type scale, radii and motion, all in `globals.css` and generated to the phone; 93 token tests; translucent text forbidden. | 2026-10-18 | ADR-086 |  | BL-19.4 to 19.6
78 | Foundations complete: icons, guards, theme control | 34 icons as pure exports, a target-size ratchet, token-adoption guard, a light/dark/device control set before first paint, and the phone's layout shift measured. | 2026-10-18 | ADR-087 |  | BL-19.7 to 19.9
79 | Form controls with inline validation | A field library (label, hint, problem beside the field, server messages by control name), checks loaded on first blur; the profile page ended 2.6 KB lighter. | 2026-10-18 | ADR-088 |  | BL-19.10
80 | Surfaces, actions, empty and status states | Card levels, button loading and soft variants, alerts that draw a shape, empty states, spinners, a gallery page; no toast by design. | 2026-10-18 | ADR-089 |  | BL-19.11, 19.12
81 | Header, footer and navigation | The current page is marked, a reduced header for sign-in, a seeker's own strip and a fixed bottom tab bar whose room is made before it arrives. | 2026-10-18 | ADR-090 |  | BL-19.13
82 | The phone's vocabulary, bar and Me tab | Phone button variants, notice shapes, list rows, an icon tab bar with the unread badge, Me as two groups of rows. | 2026-10-18 | ADR-091 |  | BL-19.14, 19.21, 19.22
83 | The phone's profile as sections, and a home that arrives once | A progress header and four profile sections each with its own Save; the signed-in home waits for four queries and holds one measured height (layout shift 0.169 to 0.002). | 2026-10-18 | ADR-092 |  | BL-19.22, 19.23
84 | The lists on one card, filters as chips | One job/course card with the organisation's mark and icon chips, filter chips as native selects, a seeker's own score on each card, a course trust strip. | 2026-10-18 | ADR-093 |  | BL-19.15 (first half)
85 | Home, vacancy, course, search and standards pages | Icon tiles, labelled fact grids, trust strips and one standard card for browse and search. | 2026-10-19 | ADR-094 |  | BL-19.15 (second half)
86 | Sign-in, sign-up, profile and apply confirmation | Field-library sign-in, 44 px targets, profile rows named for their row (17 small controls to 0), an apply confirmation that keeps what was typed. | 2026-10-21 | ADR-095 |  | BL-19.16
87 | The candidate area on the shared look | `StatusChip` (word, shape, tone) from one table per list; application, interest and saved cards; notice tiles; the account sections. | 2026-10-21 | ADR-096 |  | BL-19.17
88 | The hiring side on the shared look | Vacancy and course state chips, dashboard metric tiles, the team's role shapes; the workspace switch loaded lazily (it had been over the budget by 3.7 KB). | 2026-10-21 | ADR-097 |  | BL-19.18
89 | The back office and the static pages | One table for a complaint's state, metric tiles for the overview, marks on the legal and audience pages. | 2026-10-21 | ADR-098 |  | BL-19.19, 19.20
90 | The language and length pass | Every page loaded at 360 px in Hindi and Malay at 200% text: ten defects fixed (overflow-wrap, tab labels, score beside a title); the record of Epic B19 brought up to date. | 2026-10-21 | ADR-099 |  | BL-19.25, 19.26
91 | A designer's review and the first three fixes | Sixteen flaws found by walking the live product; fixed: the signed-in home and header, a started course is not an intake and a registered interest shows a reply date, a vacancy starts from a role; a colour preview page. | 2026-10-21 | ADR-100 |  | BL-22.1 to 22.3, 21.1
92 | Light by default, and the UX fixes that did not need a colour | The product is light whatever the device says (found because the owner's Mac was in dark mode); a public rating needs three; verified organisations read "Reviewed by our team"; the apply bar says what signing in costs. Teal, aqua and marigold were tried and the blue kept. | 2026-10-22 | ADR-101 |  | BL-22.4 (part), 22.6, 22.10

## Completed stories
Story | Title | Status | Sprint | Notes (from backlog v1.56)
BL-1.1 | Monetisation model decision | Done | 34 | ADR-025, then ADR-043 (Sprint 34).
BL-1.2 | Payment-adapter port | Done | 34 | Sprint 34. No caller yet, by design.
BL-2.1–2.4 | Match quality: configurable weights, not-interested signal, course-to-role alignment, market-wide scarce skills | Done | 33 | Sprint 33.
BL-3.1 | Assessment-provider adapter and webhook | Done | 35 | Sprint 35. Console implementation; no live partner.
BL-3.2 | Operator-verified certified skills | Done | 35 | Sprint 35. Sprint 41 added the way to link a certification to a standard.
BL-5.1 | Embedding adapter and worker sweep | Done | 36 | Sprint 36. A real sentence-transformers provider exists since Sprint 40 but is off by default.
BL-5.2 | Similarity term in the score | Done | 36 | Sprint 36. Weight is 0.0, so it adds nothing until re-tuned (BL-5.3).
BL-6.1 | SkillRelation model | Done | 36 | Sprint 36. No rows, and nothing reads it.
BL-6.5 | Store a candidate's current role | Done | 74 | Sprint 74 (ADR-084). Saved only by pressing “This is my role”.
BL-7.1–7.3 | New actors: government agency, external system, tiered operators | Done | 33 | Sprints 33 and 37.
BL-8.1–8.2 | Gig work as a Job, with completion and two-sided ratings | Done | 37 | Sprint 37. The interface was finished in Sprint 41.
BL-9.1 | Single-action ownership transfer | Done | 44 | Sprint 44 (migration 0045). Also closed a race in the last-owner rule.
BL-9.2 | Notify an organisation when its badge changes | Done | 43 | Sprint 43 (migration 0044). Email only, and only when the badge changes.
BL-9.4 | Native mobile application | Done | 62 | Built as Epic B15 (Sprints 62 to 67): mobile/ in this repository. Not yet run on a device or released.
BL-10.1–10.5 | Actor dashboards: candidate, employer, provider, operator, agency | Done | 39 | Sprint 39, with charts and drilldowns in Sprint 40.
BL-11.1–11.2 | Dashboard chart primitives and drilldowns | Done | 40 | Sprint 40.
BL-12.1–12.5 | Why not me; Hire and train; enrolled and learner notice; certification linking; gig interface and reputation | Done | 41 | Sprint 41.
BL-12.6 | Withdraw-then-reapply rule | Done | 43 | Sprint 43. A rejected or decided application cannot be withdrawn.
BL-12.7 | District skill-gap view | Done | 49 | Sprint 49 (ADR-057). Ranked by shortfall; counts under five are never shown.
BL-12.8 | Course credit chips | Done | 75 | Sprint 75 (ADR-085). Provider links the qualification; learners see it as the provider’s statement.
BL-12.13 | Role search you can trust | Done | 43 | Sprint 43 (ADR-050).
BL-12.14 | Score synonym-admitted rows in role search | Done | 45 | Sprint 45 (ADR-052). The backlog premise was partly wrong; see the story.
BL-12.15 | Operator screen for role aliases | Done | 47 | Sprint 47 (ADR-054). The screen exists; the aliases do not yet.
BL-12.16 | Browser journeys end to end | Done | 52 | Sprint 52 (ADR-062), widened to every page in Sprint 53 (ADR-064): seven journeys and an eighty-one-test route sweep. Padding that is present but wrong is not covered.
BL-12.17 | Bulk upload of vacancies and courses | Done | 51 | Sprint 51 (ADR-063, migration 0048). Check, create drafts, publish; role expansion; caps.
BL-12.19 | Bulk upload can update by external reference; a published listing keeps its standards | Done | 53 | Sprint 53 (ADR-064). Opt-in, only the columns the file carries, live listings acknowledged first.
BL-13.7 | Fix two high advisories in the production npm packages (sharp, source-map-js) | Done | 53 | Sprint 53. Four patch bumps in the lock file; the production audit is clean.
BL-14.1 | Resend a sign-in code, with a cooldown | Done | 56 | Sprint 56 (ADR-066). One cooldown for every way of asking for a code.
BL-14.2 | Replace or remove a sign-in credential | Done | 56 | Sprint 56 (ADR-066). Replace by proving the new one; remove while another verified way in remains.
BL-14.3 | Working contact and grievance forms | Done | 57 | Sprint 57 (ADR-067). A grievance is a row with a deadline, and nothing is written to an address a stranger typed.
BL-14.4 | Report a vacancy or course; operator takedown | Done | 59 | Sprint 59 (ADR-069). Reports grouped by listing; a takedown is a draft with a stamp, admin tier only.
BL-14.5 | A course has a place, a next intake and seats | Done | 58 | Sprint 58 (ADR-068). Place, intake and seats; seats left derived from enrolled interests.
BL-14.6 | Recommend courses a person can attend and afford | Done | 58 | Sprint 58 (ADR-068). Suggestions ordered by attendability, labelled and never hidden; the scorer is unchanged.
BL-14.7 | Tell the candidate what happens next | Done | 60 | Sprint 60 (ADR-070). The latest message per application, never in the outbox.
BL-14.8 | Applicant notes and a CSV export | Done | 60 | Sprint 60 (ADR-070). Private notes in the person's export; one serialiser feeds the list and the CSV.
BL-14.9 | A notification page | Done | 60 | Sprint 60 (ADR-070). Header count, paged notifications page, mark one or all read.
BL-14.10 | Upload an agency's enrolment file in the back office | Done | 61 | Sprint 61 (ADR-071). One engine for the back office and the script; the notice is attested and the attestation recorded; admin tier only.
BL-15.1 | Mobile app foundations (M1) | Done | 62 | Sprint 62 (ADR-072). Expo app in mobile/; generated client, messages and colours; sign-in. Compiled, bundled and tested (53 tests, CI job); not yet run on a device.
BL-15.2 | Browse on the phone (M2) | Done | 63 | Sprint 63 (ADR-073). Home, jobs, courses, standards, three details and search without signing in; remembered language; public-only offline cache. Browser-run, not yet run on a device.
BL-15.3 | Profile, matches and applying on the phone (M3) | Done | 64 | Sprint 64 (ADR-074). Matches with the gap and courses, apply and withdraw, save, course interest, applications with the employer's message, the profile and the role picker. Browser-run, not yet run on a device.
BL-15.4 | Alerts and account on the phone (M4) | Done | 65 | Sprint 65 (ADR-075). Updates and their count, export and deletion, contact, reporting, links. Browser-run, not yet run on a device.
BL-15.5 | Store readiness and release (M5) | Partly done | 66 | Sprint 66 (ADR-077). Code side done; the owner's accounts, bundle id, artwork, EAS project and deployment remain. Not run on a device.
BL-15.6 | Push notifications | Done | 65 | Sprint 65 (ADR-075, migration 0055). Device tokens, the worker's push sweep, an adapter with a console provider; no real vendor yet.
BL-15.7 | An old app is told to update; released operations cannot break | Done | 62 | Sprint 62 (ADR-072). 426 gate and the contract check.
BL-15.8 | A way for store reviewers to sign in | Done | 65 | Sprint 65 (ADR-076). Named phones, a fixed code, off by default, demonstration account only.
BL-15.9 | The profile's history on the phone (M6) | Done | 67 | Sprint 67 (ADR-078). Six sections through one editor checked against the schema; salary, notice, work type, alerts.
BL-15.10 | Why not me and career paths on the phone (M6) | Done | 67 | Sprint 67 (ADR-078). The rejection's gap and courses; the roles that build on one's own.
BL-15.11 | A course budget on the phone (M6) | Done | 67 | Sprint 67 (ADR-078). Held on the device, forgotten at sign-out.
BL-16.0 | UI review of the web app, the phone app and the back office | Done | 68 | Sprint 68. 29 findings, capture scripts, measurements, a workbook. Not user research.
BL-16.1 | Scannable jobs on the web and the phone | Done | 69 | Sprint 69 (ADR-079). Cards, monthly pay, paging with the server total, apply bar, trust strip, 12 px and 44 px floors, operator totals. Web and phone.
BL-16.2 | A candidate's first minute | Done | 70 | Sprint 70 (ADR-080). Task-first homepage, plain words, matches first, a match in a sentence, the phone's own home.
BL-16.5 | The employer, provider and operator screens, one design pass | Done | 73 | Sprint 73 (ADR-083); UI-26 corrected.
BL-16.6 | A real posted date on a vacancy | Done | 74 | Sprint 74 (ADR-084). Empty for vacancies published before 0057.
BL-16.7 | Newest-first vacancies | Done | 75 | Sprint 75 (ADR-085). Undated vacancies sort last.
BL-17.1 | Withdraw consent without deleting the account. | Done | 72 | Sprint 72 (ADR-082).
BL-17.2 | Ask again when the privacy notice changes. | Done | 72 | Sprint 72 (ADR-082).
BL-17.3 | Check the 18-and-over promise. | Done | 72 | Sprint 72 (ADR-082).
BL-17.4 | A privacy notice that is true, and checked against the data. | Done | 72 | Sprint 72 (ADR-082); the Hindi needs a native reader and the whole notice a lawyer.
BL-17.5 | A personal-data breach procedure. | Done | 72 | Sprint 72 (ADR-082); a draft, never exercised.
BL-19.1 | Live competitor review | Done | 76 | Sprint 76. Eight sites reviewed; docs/design/competitor-review.md.
BL-19.2 | Design brief and direction | Done | 76 | Sprint 76. Signed off by the Product Owner; docs/design/design-brief.md.
BL-19.4 | Colour ramp and semantic tokens | Done | 77 | Sprint 77 (ADR-086). Brand and neutral ramps; 93 contrast and structure tests.
BL-19.5 | Named type scale (UI-25) | Done | 77 | Sprint 77 (ADR-086). Six named steps; secondary text 15 px; Hindi line heights.
BL-19.6 | Radius, spacing, surface and motion tokens | Done | 77 | Sprint 77 (ADR-086). Radius 6/10/16, card shadow, motion and reduced motion.
BL-19.7 | Icon set for web and phone | Done | 78 | Sprint 78 (ADR-087). 34 icons; the phone’s shapes are generated from the web’s.
BL-19.8 | Theme control: light, dark and system | Done | 78 | Sprint 78 (ADR-087). Web footer and phone Me tab; no flash.
BL-19.9 | Guards for the revamp | Done | 78 | Sprint 78 (ADR-087). Target ratchet, token adoption, phone layout shift.
BL-19.10 | Form controls with inline validation | Done | 79 | Sprint 79 (ADR-088). 42 raw controls remain for the page stories.
BL-19.11 | Surfaces and actions (UI-24) | Done | 80 | Sprint 80 (ADR-089). Card levels, badge sizes, button states, alert shapes, the gallery.
BL-19.12 | Empty, loading and status states (UI-27) | Done | 80 | Sprint 80 (ADR-089). Ten empty lists; no illustration art yet.
BL-19.13 | Header, footer and navigation (UI-28) | Done | 81 | Sprint 81 (ADR-090). Marked page, reduced sign-in header, candidate strip, bottom bar.
BL-19.14 | Phone primitives | Done | 82 | Sprint 82 (ADR-091). Five button looks, success notice, danger badge, row component.
BL-19.15 | Home and discovery pages | Done | 84 | Sprints 84 and 85 (ADR-093, ADR-094). The lists, the chips, the score, the course trust strip, the home, the vacancy, course, search and standards pages.
BL-19.16 | Sign-in, sign-up, profile and apply | Done | 86 | Sprint 86 (ADR-095). Sign-in fields, full-size profile controls named for their row, the apply confirmation.
BL-19.17 | Candidate area pages | Done | 87 | Sprint 87 (ADR-096). Applications, interests, saved jobs, notices, account and career budget on the shared look.
BL-19.18 | Employer and provider workspaces | Done | 88 | Sprint 88 (ADR-097). Vacancy, course, applicant, learner, team and upload rows with shapes; dashboard tiles; workspaces loaded on demand.
BL-19.19 | Back office | Done | 89 | Sprint 89 (ADR-098). One complaint-state table for both readers; shapes on the queues; overview tiles.
BL-19.20 | Static, legal and error pages | Done | 89 | Sprint 89 (ADR-098). Marks on the audience, not-found, placeholder and legal pages; full-size choices and links.
BL-19.21 | Phone tab bar icons and unread dot (UI-18) | Done | 82 | Sprint 82 (ADR-091). Icons with the words kept; the count drawn on the Me icon.
BL-19.22 | Phone Me, home and list cards (UI-20) | Done | 82 | Sprints 82 and 83 (ADR-091, ADR-092). Me as rows; the home as one block; the cards on the type scale.
BL-19.23 | Phone profile as sections (UI-22, UI-21) | Done | 83 | Sprint 83 (ADR-092). Progress header, four sections, one Save each.
BL-19.25 | Language and length pass | Partly done | 90 | Sprint 90 (ADR-099). Hindi and Malay checked at 360 px and double text; ten defects fixed. The native Hindi reader is the Product Owner’s.
BL-19.26 | Measure and record | Partly done | 90 | Sprint 90 (ADR-099). The review is regenerated and a table added; the 52-page capture was not re-run (no test browser).
BL-21 | Epic: a more professional colour for the vocational world | Done | 92 | Added in 1.55. Closed in Sprint 92: the Product Owner kept the blue after trying three palettes.
BL-21.1 | Preview the new palette and get the Product Owner's decision | Done | 91 | Sprints 91 and 92. Palettes built and looked at; blue kept.
BL-21.2 | The new colour tokens | Closed | 92 | Sprint 92 (ADR-101). No palette change; the blue was kept. Teal build on branch theme-teal.
BL-21.3 | The colour in the assets | Closed | 92 | Sprint 92 (ADR-101). No palette change; the blue was kept. Teal build on branch theme-teal.
BL-21.4 | A review of where the brand carries meaning | Closed | 92 | Sprint 92 (ADR-101). No palette change; the blue was kept. Teal build on branch theme-teal.
BL-21.5 | Verify and record the theme | Closed | 92 | Sprint 92 (ADR-101). No palette change; the blue was kept. Teal build on branch theme-teal.
BL-22 | Epic: user experience remediation | Partly done | 91 | Added in 1.55. BL-22.1 to BL-22.3 done in Sprint 91; BL-22.6 and BL-22.10 done and BL-22.4 partly in Sprint 92.
BL-22.1 | The home and the header know who is signed in | Done | 91 | Sprint 91 (ADR-100). Done in Sprint 91 (ADR-100).
BL-22.2 | A started course is not an intake, and a registered interest says when to expect an answer | Done | 91 | Sprint 91 (ADR-100). Done in Sprint 91 (ADR-100).
BL-22.3 | Start a vacancy from a job role | Done | 91 | Sprint 91 (ADR-100). Done in Sprint 91 (ADR-100).
BL-22.4 | Trust is shown as the good: verification and ratings | Partly done | 92 | Sprint 92 (ADR-101). Rating threshold and verified line done; the quiet unverified line needs a report count.
BL-22.6 | The apply bar and the filter row | Done | 92 | Sprint 92 (ADR-101).
BL-22.10 | The product is light by default, whatever the device says | Done | 92 | Sprint 92 (ADR-101). Found by a request for a whiter page.